## Sheet1
User Story Id | Title | Description | Acceptance Criteria | Dependencies | Completed | Story Type
1 | Install and Configure Kafka | Install Kafka server on your machine and check if Zookeeper and Kafka is starting or not . | * Kafka server installation must be completed. * of Kafka server should be done, details like server port for Kafka and zookeeper. | Docker must be setup and running in your machine | Yes | Technical
2 | Create and Configure Kafka Topic | Create Kafka topics based on applications for better maintainability | *Configuration for Kafka topic must be done in Kafka server properties based on applications. *OSS must have a topic as "OSSTOPIC" *Incident manager should have it as "IMTOPIC" | Kafka must be up and running. User Story 1 | Partially | Technical
3 | Create a Service which can Receive Kafka Message | Create a Service which will consume messages from Kafka topic and process based on needs | A new service must be created which can: *Receive Message from Kafka Producer from different applications. *Process message from various applications | Kafka Topic must be configured. User story 2 | Yes | Technical
4 | Receive Mesaage from Kafka for events via Service | Run the service to process messages coming from Kafka Producers. | Service must have a Consumers which can: *Kafka consumer should consume messages from various topics. *Kafka Consumer should be able to accept various type of beans from Consumers as JSON messages and process as needed. | Service and Kafka must be up and running. User story 3 | Yes | Technical
5 | Create Slack Workspace and app | Slack workspace, app and webhook is important to send or receive message from any service. | * Slack workspace and app is created ready to receive Message. *Webhook for Slack is created to receive message on specific channel using webhook URL |  | Yes | Technical
6 | Check Slack connectivity | Check if Slack server can receive messages on UI. Try to add users in slack App or conversations | *Service must be able to identify the messages to be sent to Slack based on Flags. *Slack must be configured to receive messages *Users must subscribed or added to app to see messages coming from Different applicartion. | User story 5 | Yes | Technical/Functional
7 | Send Slack message based on the event generated | Slack workspace, app and webhook must be able to receive messages | *User should be able to see the Slack messages for particular app. *In order to see notification on Slack. User must be subscribed or added to Slack App to be informed of some event. | User story 3 | Yes | Technical
8 | Create emails based on messages received and send to user | Emails must be based on events generated from Producer. | *Service should be able to receive events via consumers and act based on business logic to send emails. *User must be able to receive notifcations in proper format and with proper data. |  | Yes | Technical
9 | Configure Slack to receive message on different chats. | Configure different chats and send messages to chats | Application must be able to send message to different chat Groups rather than whole app to better manage the events. |  | Future Backlog | Technical/Functional
9 | Send Rich text or HTML emails/Messages using templates for better look and feel | Send emails based on templates. | *Application should be able to send HTML message with the help of templates to have uniform look and feel of email. *These emails should have information about various events based on applications. |  | Future Backlog | Function/User
10 | keep track of failed message with DB | Track all failed messages based on message Id which were not receieved by service or for which Email or message was no sent. | Keep a track of all failed messages in SQL or NOSQL DB. |  | Future Backlog | Technical
11 | Retry failed messages. | Have a machanizm to retry failed messages manually or automatically. | Have a cron scheduler to retry failed messages in a particular time interval. |  | Future Backlog | Technical
12 | Create rest service to receive data from applications in specific format | Receive data from different applications in the form of JSON data which can include basic details and flags to process business logic. | Receive data from applications in form of dffiferent objects specific to application or in Generic Json Format. |  | Future Backlog | Technical
13 | Reporting to check success and failed messages | Reporting system to see reports | have a reporting system to check the message statues and generate report of same. |  | Future Backlog | Functional/User
14 | Include other channels like SMS or whatsapp | SMS and whats app features must be added. | As a service, We should also extend support for other channels like SMS or whatapp to send notifications on timely bases based on event. |  | Future Backlog | Functional/User
15 | Keep the system generic so any new application can be configured easily. | New application can be added wihout much efforts. | Any new application must be able to configure to send email from my application without much development efforts from the application.
16 | Business logic for applications to leverage the new service. | Special logics to handle based on applications. | In case if any special handling of messages/events is required from any application, The service shoould be able to handle. |  | Future Backlog | Functional/User
17 | Translated messages | Have translation for messages/emails to have better experience for user. | As a user of any Application, I should be able to receive the notifications/message in my preferred language. |  | Future Backlog | Functional/User
18 | Enable Security | Have a secure way to send notification. | As a service, we need to include all security and encryption details to the communications sent |  | Future Backlog | Technical

## Sheet2
5 | Create Slack Workspace and app | Slack workspace, app and webhook is important to send or receive message from any service. | * Slack workspace and app is created ready to receive Message. *Webhook for Slack is created to receive message on specific channel using webhook URL |  | Yes | Technical
6 | Check Slack connectivity | Check if Slack server can receive messages on UI. Try to add users in slack channel or conversations | Slack must be configured to receive messages | User story 5 | Yes | Technical
7 | Send Slack message based on the event generated |  | User should be able to see the Slack messages for particular channel provided. In order to see notification on Slack.. User must be subscribed or added to Slack channel to be informed of some event. |  | Yes | Technical